## Sheet1
Production Planning - Gantt Chart
Task Name | Duration | Start | Finish | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Planning
Read, analyse and condense the brief into personal notes | 1 Day | 2020-11-02 | 2020-11-02
Create a production plan (Gantt Chart) | 1 Day | 2020-11-03 | 2020-11-03
Research 'impossible staircase' and other illusionary artwork | 1 Day | 2020-11-04 | 2020-11-04
Consolidate a small list of artistic influences | 1 Day | 2020-11-05 | 2020-11-05
Research the physics behind a bouncing ball and how it iteracts with certain materials | 1 Day | 2020-11-06 | 2020-11-06
Design
Create annotated diagrams/drawings, experimenting with different design ideas | 3 Days | 2020-11-09 | 2020-11-11
Test colour palettes | 1 Day | 2020-11-12 | 2020-11-12
Create annotated, finalised diagram/drawing | 1 Day | 2020-11-13 | 2020-11-13
Plan and collect/create necessary required textures | 1 Day | 2020-11-16 | 2020-11-16
Identify and plan where and how MEL/Python scripts will be used to generate geometry | 1 Day | 2020-11-17 | 2020-11-17
Plan where to incorporate the bouncing ball animation and how it will interact with the environment | 1 Day | 2020-11-18 | 2020-11-18
Development
Create 3D model of environment | 2 Weeks | 2020-11-23 | 2020-12-04
Animate the bouncing ball | 1 Week | 2020-12-07 | 2020-12-11
Add environment details | 3 Days | 2020-12-14 | 2020-12-16
Texture the 3D model | 3 Days | 2020-12-17 | 2020-12-21
Setup scene lighting | 1 Day | 2020-12-22 | 2020-12-22
Render a test sequence | 1 Day | 2020-12-23 | 2020-12-23
Check entire seen and make any necessary changes | 1 Day | 2020-12-24 | 2020-12-24
Render final sequence | 1 Day | 2020-12-25 | 2020-12-25
Contingency | 1 Week | 2020-12-28 | 2021-01-04